## Instructions
Instructions and Use for Example Workplan - Specimen Referral System: This is an example of a costed workplan that can be used to plan and track activities and expenditures against a budget. Sample activities that should be included are listed, but should not be treated as exhaustive and exact activities will depend on the nature, maturity and scale of the specimen referral network. The workplan should be developed as an iterative and consensus-building activity but needs to have roles and precise responsibilities to ensure that the activities are carried out. There should also be one individual or department within the Ministry of Health (MoH) who is in charge of following up on all activities and budgets/expenditures.
Sections of the Workplan |  | Actions
| Column A refers to one of the six phases of a specimen referral network | There are six phases of a specimen referral system from (1) Detailed situational assessment of current specimen referral systems to (6) Ongoing monitoring and evaluation, and continuous improvement. All planned activities are placed in one of these phases.
| Column B refers to the components of a specimen referral system that are involved in this activity | There are six components of a specimen referral system, similar to the six WHO building blocks of a health system. All planned activities are associated with one or more of these components
| Column C refers to the planned activity and references useful tools for this activity | This column already has planned activities included, with reference to useful tools from the Specimen Referral Toolkit (tools listed in "Useful Tool References" tab) but should not be limited to these activities. Write additional activities or details as needed.
| Column D refers to the timelines or timeframes of the activity | Write the timelines or timeframes of the activity here. Suggestions are included but may vary depending on the setting and system
| Column E refers to the reponsible party or parties and roles | Write the party or parties that is/are responsible for the activity and if there are multiple parties, please specify roles
| Column E refers to the outputs and results of the planned activity | Write the desired outputs or results of the activity here. Suggestions are included but may vary depending on the setting and system
| Column F refers to the approximate costs or budget of the planned activity | Write the approximate cost or budget for this planned activity based on quantity, frequency and unit costs.
| Column G refers to the actual expenditure of the activity once it is carried out | After the activity is initiated up to when it is complete, write down the actual expenditure at various stages.
| Column H refers to the % of the budget that was spent | This calculation shows how much (%) of the budget is currently spent
| Column I refers to the balance of the budget that is remaining | This calculation shows how much ($) of the budget is remaining
| Column J refers to any additional comments on the activity | Write any other comments or progress here

## Specimen Referral Workplan
Setup and Implementation Workplan - Specimen Referral System
Phase | Component | Planned activities (with reference to relevant tools in Specimen Referral Toolkit) | Timelines | Responsible Party/-ies and Roles | Outputs/results | Approx. cost/budget | Expenditure | % of budget spent | Budget balance | Comments
Phase 1: Detailed situational assessment of current specimen referral systems | 3 | Landscape assessment1, 2, 11, 12 | 4 weeks: 1-2 weeks on the ground plus 2-3 weeks of due diligence and report writing |  | Shared report of specimen referral landscape in a country |  |  | #DIV/0! | 0
| 1 | Setup of integrated specimen referral technical working group as an offshoot of a laboratory or logistics TWG - the first meeting of which should be a stakeholders' meeting to discuss assessment report14 | 1 week to setup and plan then half-day every 2 months to start (more frequently if needed) - first meeting soon after landscape assessment report is submitted |  | Group that can discuss and advise on all specimen referral systems in a country |  |  | #DIV/0! | 0
Phase 2: Design of a specimen referral system pilot | 1,4 | Appointment of individual AND department to oversee specimen referrals within MoH | 1 day, the sooner the better to have someone in place early on for management and continuity purposes |  | Individual and department within the MoH assigned to oversee specimen referrals
| 6 | Laboratory and route network optimizations, including integration of various specimen types, wherever possible7 | 4-6 weeks: 1-2 weeks on the ground plus 3-5 weeks of offsite data analysis |  | Final referral laboratories determined and mapped; routes to reach the referral laboratories from the health facilities mapped and optimized |  |  | #DIV/0! | 0
| 1 | Development of specimen referral strategy or policy at national level that provides a long-term vision of specimen referral design, oversight, and performance and guides strengthening initiatives14 | 2-3 months |  | A strategy or policy document to guide the specimen referral networks at a national level |  |  | #DIV/0! | 0
| 2 | Determine a high-level budget to use to explore potential funders and funding mechanisms, depending on the proposed structure of the referral network (i.e. if outsourced); and then will cost out a more detailed workplan9 | 3-4 weeks with possible one-on-one or larger donor meetings, and will include results of the laboratory and route network optimizations |  | Detailed and high-level budget and workplan that can be used to guide activities and used to advocate for funds, which will be secured |  |  | #DIV/0! | 0
| 1,3 | Develop M&E framework and strategy, including key performance indicators (KPIs)13, 14 | 3-4 weeks |  | M&E framework document that will plan for M&E as well as data tools, data collection (frequency and what to include), etc.
| 1 | Tendering of services, awarding of service provider, negotiation and signing of contract | 3-6 months including advertising time and review of applications |  | A transparent and competitive bidding process ending in a fairly awarded contract with a suitable service provider |  |  | #DIV/0! | 0
Phase 3: Setup and implementation of pilot | 3 | Print and provide all logbooks, guidelines and other documents to ST couriers and stakeholders4, 5, 6, 7 | 2-4 weeks, depending on printing time and printing/delivering mechanism |  | All data collection tools are available to those who will fill them out |  |  | #DIV/0! | 0
| 4 | Training of service provider (courier), including biosafety/biosecurity training14 | 1 day centrally and then time to train the couriers in the regions |  | Couriers are trained on how to properly and safely handle potentially-biohazardous materials |  |  | #DIV/0! | 0
| 5 | Procurement of equipment and supplies including packaging14 | Depends on local or international procurement and border clearing times |  | All sites will have access to proper packaging using approved equipment |  |  | #DIV/0! | 0
| 4 | Training and sensitization of health facilities and laboratories and ensure all stakeholders have a copy of the ST schedule7 | 4+ weeks depending on the size of the country and size of the system and the number of training teams |  | All sites will understand how to properly package specimens, when to request for tests and know when their pickups will be |  |  | #DIV/0! | 0
| 6 | Pay monthly courier costs | Likely invoiced on a monthly basis after the service is provided |  | Costs are paid for, according to an invoice, on a monthly basis |  |  | #DIV/0! | 0
| 3 | Monthly data reporting by health facilities and laboratories8 | Monthly basis, likely due on the 5th day of every month |  | All reports are collated and submitted to the central MoH oversight body on a monthly basis |  |  | #DIV/0! | 0
Phase 4: Review of pilot | 1 | Supervision and management visits2, 11 | Every 2-3 months; possibly more frequently at the start |  | The central MoH oversight body provides regular supportive supervision using a standardized data collection tool and provides sites feedback |  |  | #DIV/0! | 0
| 1 | Biosafety, biosecurity and quality control are monitored by the laboratory quality department/ team14 | Every 2-3 months; possibly more frequently at the start |  | The laboratory QA unit ensures biosafety and biosecurity of the system
| 1 | M&E officer visits sites every 3-6 months to collect/verify data and then analyse to inform operational processes and to share information with partners2, 11, 13, 14 | Every 3-6 months |  | Data is complete, verified and analyzed, then shared with TWG to inform decision-making |  |  | #DIV/0! | 0
| 1 | Contract management including monthly meeting with service provider to discuss performance and challenges2, 13 | Monthly basis |  | Direct communication between service provider and contract manager is regularly made |  |  | #DIV/0! | 0
| 1 | Stakeholders meeting to discuss progress | 1 day |  | TWG reviews progress of specimen referral system |  |  | #DIV/0! | 0
Phase 5: Scale-up of the specimen referral system | 1 | Stakeholders meeting to discuss scale-up | 1 day |  | TWG makes decisions on future scale-up, integration, etc. |  |  | #DIV/0! | 0
|  | Other activities depending on the scale-up decisions made by the TWG/stakeholders | NA |  | NA |  |  | #DIV/0! | 0
Phase 6: Ongoing monitoring and evaluation, and continuous improvement | 3 | Refresher training | 4+ weeks depending on the size of the country and size of the system and the number of training teams |  | All sites and couriers will be reminded how to properly package and transport specimens, when to request for tests and know when their pickups will be |  |  | #DIV/0! | 0
|  | Other activities depending on the scale-up decisions made by the TWG/stakeholders | NA |  | NA |  |  | #DIV/0! | 0
|  | 12-18 months' activity |  |  | SUB-TOTAL | 0 | 0 | #DIV/0! | 0

## Useful Tool References
Reference from Workplan | Tool from Specimen Referral Toolkit
1 | ASLM Questionnaire for Countries – Specimen Referrals
2 | Courier or Specimen Transport Manager questionnaire
3 | Example Workplan – Specimen Referral System
4 | Individual Specimen and Results Tracking Log
5 | Referral Laboratory Specimen Reception Log
6 | Referring Facility Specimen Referral Log
7 | Schedule and Routing Chart for Specimen Transportation
8 | Specimen referral data summary collection form
9 | Specimen Referral System Budget Tool_v1.0
10 | Specimen Referral System Dashboard
11 | Specimen referral _subnational_checklist_final
12 | SR Compass Questions
13 | M&E framework (M&E Framework)
14 | GLI Guide to TB Specimen Referral Systems and Integrated Networks

## Component Codes
Code | Component
1 | Management (including Strategic Planning & Performance Management)
2 | Financing and costing
3 | Data collection, monitoring and evaluation
4 | Human Resources
5 | Equipment
6 | Network design, scheduling and transportation