Progress Report 5

Global TB Drug Facility

Period:   1 July  –

31 December 2003

The Stop TB Partnership Secretariat

Geneva, Switzerland

March 5, 2004

Table of Contents

Page

Executive Summary 										4

Grants	Applications and Review								5

Drug Management										5

Procurement											5

Novartis Donation										6

Pre-qualification of Manufacturers of TB Products						6

GDF Products											6

Direct Procurement Service									7

Monitoring											7

Phase out  strategy										7

Case History for the GDF Comprehensive Package of Services 				8

Advocacy and Communications								8

The GDF and GFATM: a Growing Partnership						8

GDF TAS system										9

GDF Operations and Management								9

Appendix

1) Cumulative Statement of Income and Expenditures 2003				11

2) Details of GDF Country Support Performance and Impact Indicators			13

Acronyms

AMDS--AIDS Medicines and Diagnostics Service

GDF--Global TB Drug Facility

GFATM--Global Fund to Fight HIV/AIDS, TB and Malaria

GMP-- Good Manufacturing Practices

GLRA -- German Leprosy and Tuberculosis Relief Association

HTM-TAS--HIV/AIDS, TB and Malaria Treatment Access System

IAPSO--UNDP Interagency Procurement Services Office

KNVC--Royal Netherlands Tuberculosis Association

LICB--Limited International Competitive Bid

MMSS--Malaria Medicines and Supplies Service

MOU--Memorandum of Understanding

MSH--Management Sciences for Health

SOPs--Standard Operation Procedures

TAS-- Treatment Access System

TRC--Technical Review Committee of the GDF

WHO/EDM--WHO Department of Essential Drugs and Medicines

WHO-- World Health Organization

4FDC--the four-drug FDC tablet

Global TB Drug Facility

Progress Report 5

Period:   1 July - 31 December 2003

Executive Summary

The Global TB Drug Facility (GDF) helps countries expand DOTS in their national TB programs and fill in the procurement, supply or technical gaps. This report covers activities and programs of the GDF from 1 July - 31 December 2003.

During this period, the GDF made important progress with the completion of the seventh round of grant applications. The Technical Review Committee met on 16-18 September and reviewed a total of thirteen country applications; seven new applications from country programs, three resubmitted country program applications, and three from country programs which are being monitored for second year support.  The TRC approved seven new applications for support (Algeria, Cambodia, Equatorial Guinea, Niger, Syria, Turkmenistan, Zambia) and three other countries (Togo, Nigeria, and Sudan) for second year support. This raises the number of countries and NGO’s approved for GDF support to 58 applicants and 49 countries.  In the important area of procurement 40 countries received life saving anti-TB drugs with another nine scheduled for delivery for early 2004.

The Direct Procurement Service set a new precedent with the Philippines placing a $4.4 million US dollar order, with funding from the World Bank.  In this reporting period alone, more than nine countries have taken advantage of the Direct Procurement Service placing drug orders for more than 471,000 patients at an estimated value of more than $6 million US dollars. It is hoped that this progress will continue and that the Direct Procurement Service will expand to assist countries with their  procurement needs.

The GDF completed and published the first edition of its “White List,” also known as The GDF Catalogue of Approved TB Products and Manufacturers.  This White List will facilitate access to anti-TB drugs of acceptable quality, through the assessment of products and manufacturers for compliance with WHO recommended standards for quality and good manufacturing processes.   The publication of this list comes at an important time, as efforts are made to improve drug quality globally and to reduce the development of MDR-TB.

An important new tool for TB treatment completed field tests and will soon be put into service.  The GDF/ Stop TB Patient Kits – one kit for Categories I and III treatment and a second kit for Category II treatment were produced and successfully field tested during this report period. Each kit contains a full course of treatment and uses only fixed dose combination tablets. This kit will be an effective tool in advancing DOTS treatment regimes and help improve TB pharmaceutical management and logistics.

In the area of partnership building, the GDF and Novartis signed a Memorandum of Understanding under which the Novartis Foundation  will donate one half-million patient kits of drugs to the GDF. This donation represents the first time a major pharmaceutical manufacturer partnered with the GDF and the Stop TB  Partnership to supply free patient kits. Other partners like KNVC, IUATLD, WHO, MSH and GLRA continue to provide important monitoring, evaluation and desk auditing support.  Without these and other partners, the ability of the GDF to provide technical support to countries would be greatly diminished.

Appendix 1 gives the financial statement for the GDF and appendix 2 gives the program indicators.

#### The Global TB Drug Facility: Securing Access to High Quality Anti-TB Drugs.

Grant Applications and Review

The Global TB Drug Facility (GDF) continues to meet the immediate needs of countries for anti-TB drug grants. The Technical Review Committee met on 16-18 September and reviewed a total of thirteen country applications; seven new applications from country programs, three resubmitted country program applications, and three from country programs which are being monitored for second year support.  The TRC approved seven new applications for support (Algeria, Cambodia, Equatorial Guinea, Niger, Syria, Turkmenistan, Zambia) with three countries (Togo, Nigeria, and Sudan) approved for second year support.  See Table 1. One country was not approved and two were placed under consideration. So far, the GDF has approved grants of 2.3 million patient treatments to 52 countries.

Table 1: 7th TRC accepted applications

| Country | Total patients |  | Total Cost, USD |
| --- | --- | --- | --- |
| Algeria | 9,800 |  | 258,720 |
| Cambodia | NA |  | 110,773 |
| Equatorial Guinea | 660 |  | 174,240 |
| Nigeria | 35,000 |  | 462,000 |
| Niger | 9,200 |  | 242,880 |
| Sudan | 12,000 |  | 158,400 |
| Syria | 500 |  | 13200 |
| Togo | 1,644 |  | 21,700 |
| Turkmenistan | 10,831 |  | 285,938 |
| Zambia | 50,000 | 1,320,000 |  |

The main beneficiaries of GDF grants continue to be low-income countries (per capita GNP below$1,000) that fulfil the GDF conditions of support.  Lower-middle income countries with a per capital GNP below $2,995 are also eligible.  The GDF is working with countries to encourage future grant applications, where appropriate, and transition those with current three year grant commitments to other GDF services to secure the gains in drug quality, procurement and pharmaceutical management after the expiration of their grant.

The GDF continues to develop new and more efficient ways of streamlining the grant application screening process for TRC members and other assessment purposes.  The Mayetic Village, a shared secure website, continues to enable TRC members to review, comment and vote on emergency and monitoring applications online.  The GDF is considering improvements to this web site in response to feedback from TRC members and other relevant parties.

Drug Management

Assessments of the drug distribution system continue to be carried out as part of all GDF country and monitoring visits.  These assessments also include a list of program recommendations needed to advance good drug management practices for consideration by the National Tuberculosis programme, key partners and the WHO/EDM. The GDF also developed a drug management assessment tool and drug management indicators to help catalyse work in drug management with key Stop TB Partners.

In October 2003, GDF and MSH jointly hosted a TB drug management symposium at the 2003 IUATLD Annual Congress. A status report describing improvements in TB drug management by participating programs, since the 2002 RPM Plus/GDF/SEAM Washington Conference, has been developed and posted on the MSH website.

Procurement

The GDF continues increasing the amount of TB drugs and products delivered to countries.  During this period, the GDF delivered 420,688 patient treatments to 14 countries at a total estimated value of $4,340,541.  Cumulatively 52 applicants have received GDF drug deliveries.

During this report period another procurement milestone was reached with the successful completion of the GDF’s second internationally competitive selection process for procurement agents.  Finalised in October 2003, the process saw the reappointment of UNDP Interagency Procurement Services Office as the GDF’s procurement agent. The contractual relationship between the GDF and IAPSO for procurement services will allow the GDF to continue its streamlined and innovative procurement process.  Securing IAPSO as the GDF’s procurement agent paved the way for the launch, in October 2003, of a second global Limited International Competitive Bid (LICB) involving various pre-qualified pharmaceutical manufacturers of anti-TB drugs.

This LICB, when successfully completed, will allow the GDF to have at least two pharmaceutical manufacturers to satisfy the GDF’s procurement needs.  A key component of this tender offer is the inclusion of GDF Patient Kits (see products section below for more information) to enhance supply and service to DOTS programs. The GDF will also launch an International Request for Proposals from Pre-shipment and Quality Control Agents in the second quarter of 2004. The current GDF pre-shipment inspection and quality control agent, SGS Nederland BV (formerly SGS Global Solutions), will compete with other agencies for pre-shipment inspections and laboratory analyses to ensure quality control. As a part of this process Kuhne, Nagel & Mahé will continue to provide air and sea freight forwarding services as subcontractors of UNDP/IAPSO contract.

Photo: Mario Raviglione, Director Stop TB Department, WHO, Daniel Vasella, Chairman and CEO, Novartis AG, and Virginia Arnold, GDF Operations Manager, STB Partnership.

# Novartis Donation

On December 19th 2003 Novartis and WHO signed a Memorandum of Understanding (MOU) under which Novartis will donate a half-million  patient kits worth of drugs valued at over US$ 7 million.  This donation marks the first time a major pharmaceutical manufacturer donated drugs to GDF.

# Pre-qualification of Manufacturers of TB Products

The GDF completed and published the first edition of its “White List,” also known as The GDF Catalogue of Approved TB Products and Manufacturers, a culmination of over two years of collaboration with the WHO/EDM which aims at facilitating access to anti-TB drugs of acceptable quality, through the assessment of products and manufacturers for compliance with WHO recommended standards.   This list allows suppliers with pre-qualified status to participate in every LICB.  It also offers countries, NGOs and donors the option to purchase high quality TB drugs and products directly from the manufacturer.  Suppliers will still have to be re-qualified every three years and the GDF will continue with independent quality control procedures for all shipments to GDF consignees.  The GDF will constantly update this list as new suppliers, locations and products as they are approved.

Products

Photo: GDF’s TB Patient Kit

Progress continues on the development and marketing of the GDF TB Patient Kits.  Two prototype GDF Patient Kits – one for Categories I and III and a second for Category II – have been produced and successfully field tested in Kenya. Each kit contains a full course of treatment and uses only fixed dose combination tablets. Use of FDC should enhance rational drug treatment because all drugs will be available in the appropriate dosages and quantities.

The Stop TB Partnership continues to promote the use of FDCs and in particular the four-drug FDC tablet.  The GDF continues to advocate for the use of 4FDCs given the lack of product standardization in many TB programs.  To assist countries with the introduction of 4FDCs into their country programs, a book on drug management and standardization was recently published.  This book, entitled “Operational Guide for National Tuberculosis Control Programmes on the Introduction and use of Fixed-Dose Combination Drugs” (WHO/CDS/TB/2002.308), and other aspects of 4FDC orientation are now included in materials presented on all GDF country visits.

In December 2003, GDF provided speakers and consultants to a WHO/EDM international meeting on the use of fixed dose combination products for multiple health problems including TB, HIV and malaria. The history of FDCs in TB and the experience of the GDF in providing access to quality FDCs were profiled.

# Direct Procurement Service

During 2003, eleven countries took advantage of the Direct Procurement Service placing orders for more than 471,000 patients treatments at an estimated value of $6 million US dollars.  In November 2003, the Philippines alone sets a precedent with its $4.4 million US dollar order, with funding from the World Bank.

## Value of GDF Direct Procurement Direct Orders

| Country (funding source) | US$ | Patient Treatments Approved |
| --- | --- | --- |
| Afghanistan (WHO)*** | 467,347 | 38,190 |
| Armenia (KFW)* | 55,440 | 4,200 |
| Bangladesh (WHO) | 22,801 | 5,500 |
| Cambodia (JICA)** | 36,607 | N/A |
| East Timor (Caritas Norway) | 41,580 | 3,150 |
| Georgia (KFW) | 89,155 | 10,100 |
| Iraq (WHO)*** | 316,982 | 18,000 |
| Nepal (WHO/DFID) | 494,771 | 43,316 |
| Nigeria (NLRA) | 92,730 | 7,025 |
| Philippines (World Bank)*** | 4,383,404 | 340,000 |
| South Sudan (WHO) | 22,127 | 2,500 |
| Totals | $6,022,944 | 471,981 |

*German Bank for Reconstruction and Development

**Government of Japan.

*** Order placed during current report period.

The GDF continues marketing this service to countries, national TB control programs, WHO representatives, GFATM portfolio managers and others in an effort to increase the number of countries using Direct Procurement Service.  The GDF and the Stop TB Partnership hopes it can further drive down costs, increase quality and improve procurement efficiency through grant and direct procurement services.

Assisting the GDF with its marketing effort is a volunteer marketing team from Procter & Gamble who is developing a strategy to increase the number of countries taking advantage of the Direct Procurement Service for their TB supply needs.

# Monitoring

During this report period, the GDF/Stop TB Partnership completed 10 monitoring visits with another 19 planned for the first six months of 2004.  This is the most monitoring visits ever undertaken in the history of the GDF.  At the same time, the number of desk audits completed, by partners, MSH and GLRA increased to 13 (eight by MSH and five by GLRA).

As a result of increased demand for GDF monitoring services and TRC review requirements, the GDF reduced the gap between drug deliveries and monitoring trips from eight months to six.  It also improved the In-Country Monitoring Checklist. This form will become standard in all future country monitoring visits and should enhance the quality and quantity of monitoring data gathered.

Developing a Phase-Out Strategy:  Securing the Gains

During this period, the GDF initiated a phase out strategy for countries nearing the end of their grant period. GDF’s mandate only allows for the GDF to provide up to three years of support for countries receiving grants.  Following this period, countries have three options:  1)  re-apply for another three year grant (subject to resource availability); 2) continue to access GDF products and services through the direct procurement service, or 3) select a different organization for their drug procurement and management services. The underlying principle of the GDF phase out strategy, is that it should be responsible i.e. that phase out from grants should not harm the program and that any “GDF gains” made in terms of DOTS expansion, product standardization, quality or cost should not be hampered in the process of phasing out from grants.The GDF/Stop TB Partnership team carrying out  the third  year monitoring missions to grantees, examine country plans and assist countries with exploring their options.

The GDF Comprehensive Package of Services

In the autumn of 2003, the GDF decided to make greater use of a bundle approach to its functions and services.  The Secretariat believes that by providing packages of services (Grants, Direct Procurement Service, white list of manufacturers a.k.a the Catalogue of Approved TB Products and Manufacturers and other technical support for drug management and monitoring) under the GDF umbrella it can better serve their needs.  The case of the Philippines serves as a good example for the GDF’s bundled approach as it is a high TB burden country and the support it received from the GDF highlights the full spectrum of services and support, currently offered by the GDF:

The Philippines benefit from using the GDF “bundled approach”

- Awarded an emergency grant comprising 69,500 patient treatments to meet a procurement short-fall (Aug 2003). An example of timely supply.

- Awarded a three-year grant to support a Private-Public Partnership (10,000 patient treatments delivered June 2003).  Grant support for innovative partnerships in TB control.

- Using a World Bank loan and the GDF Direct Procurement Service, the Philippines procured 340,000 GDF Patient Kits worth approximately US$ 4.4 million.  This will be the first country to receive the new kits in June 2004.  The largest Direct Procurement order to date and an important culmination of World Bank support for the GDF model, which should serve as a good example for the introduction of the GDF's new product line of GDF Patient Kits.

- Technical and drug management support to Philippines has come from the GDF Secretariat, WHO and MSH. Logistics support has come from the GDF Procurement agent, UNDP/IAPSO.  Many partners working as one in an efficient and innovative manner.

- Supply of the GDF Patient Kits will be from a manufacturer found to be operating at an acceptable level of compliance with WHO Good Manufacturing Practices (GMP) as assessed by inspection teams convened by EDM as a part of the TB pre-qualification project highlighted above.  An example of use of the white list

### Advocacy and Communications

In December 2003, the Stop TB Secretariat hired a Communications Manager to its staff and began working on designing and re-branding the GDF with volunteers from Proctor and Gamble.  The GDF and P&G began exploring new ways of enhancing and modifying its visual representation to improve marketability. The GDF’s three service lines (Grants, Direct Procurement Service and the White List a.k.a the Catalogue of Approved TB Products and Manufacturers) as well as technical assistance/capacity building for drug management and programme monitoring are being examined to better illustrate the range of GDF services and promote partnership.

### The GDF, the Stop TB Partnership and the Global Fund to Fight HIV/AIDS, TB and Malaria: a Growing Relationship

The GDF continues to formalise links with the GFATM through the Stop TB Partnership. These links include the following:

- The GFATM Secretariat has been invited as an observer to Stop TB’s Co-ordinating Board and Technical Review Committee meetings.

- The Green Light Committee is the authoriser of second line TB drugs to the GFATM.

- All Co-ordinating Board decisions on GDF grants are reported to the GFATM Secretariat.

- Three GFATM Technical Review Panel members for TB are members of the GDF’s TRC.

- GFATM Fund portfolio managers are copied all GDF country and monitoring visit reports.

- GDF staff  participate in GFATM  regional meetings, when invited.

- GDF staff have met with GFATM portfolio managers to explain GDF mechanisms and sent them the direct procurement flyer.

Representatives of the GFATM and the Stop TB Partnership continue to meet regularly and explore collaborative approaches. Work continued on developing a Memorandum of Understanding between the Stop TB Partnership and the GFATM.  It is hoped that this MOU will clear the way for greater use of the GDF as a source for TB drug procurement and support services by GFATM countries.

The GDF and GFATM, also developed a flyer explaining the services and advantages of using the GDF to support countries in securing life saving TB medicines and products.  Distribution of this flyer is currently under way to countries applying to the GFATM seeking support as well as principal recipients of those countries already approved for support.

### GDF TAS system

### Access to quality treatment for HIV/AIDS, TB and malaria must be rapidly improved if WHO and its members and partners are to reach the goals for the three diseases.  An HIV/AIDS, TB and Malaria Treatment Access System has been set up in WHO, to improve the supply of core commodities for the three diseases and expand treatment.  Based in WHO/HTM, the TAS is comprised of representatives of the GDF and parallel mechanisms for HIV/AIDS and malaria.  An AIDS Medicines and Diagnostics Service has been established as the access and supply arm of the WHO-UNAIDS 3 by 5 initiative.  The Roll Back Malaria Partnership is working towards the launch of a Malaria Medicines and Supplies Service.  The GDF, AMDS, and MMSS will work independently, but will collaborate on harmonizing or pooling functions where this benefits all of the disease initiatives.

### GDF Operations and Management

Internal Organization

In August 2003, the GDF secretariat held their second formal retreat of the year  in order to prepare the 2004-2005 work plan and to prepare for the IHSD evaluation. The outcome of this retreat was a full SWOT analysis for each of the operational areas of the GDF Secretariat and a draft work plan. The work plan was further modified in the fall and endorsed by the Stop TB Co-ordinating Board in December 2003.

During this period, the filing system for hard copy documents was revised and streamlined within the WHO system. Likewise preparations were made to use a new electronic filing system including the filing of e-mails and scanned copies of incoming mail. This system will also allow to search and retrieve electronic copies.

An assignment was given to the Management Information Systems of WHO to do an in depth analysis of the GDF and the GLC which will result during 2004 in the identification and finally the implementation of a common and intuitive information management interface to the GDF/GLC processes for all staff.

A parallel process was started to re-formulate the current Standard Operation Procedures (SOPs) of the GDF, which will lead to a ISO 9001:2000 certification of the GDF. Proposals were requested to identify an external consultant to guide the GDF through this process.

#### Donor Support

During this period commitments from CIDA USAID and Government of Japan  were secured.  A new donor - the Government of Norway pledged additional funds to help close the remaining 2003 funding gap (see Appendix 1). The funding gap for 2004 has been significantly reduced due to continued support of commitments of USAID, Netherlands Government, CIDA, Norway and others.

##### GDF/GLC convergence

In December 2003, the first “joint” GDF/GLC country visit took place with a visit to the Philippines and the pre-qualification project for first line drugs, has also expanded to include second line drugs. Work relating to the convergence of the GDF/GLC continued in the period under review in order to formalise appropriate arrangements in due course.

##### IHSD Evaluation

The GDF was profiled in the recent IHSD evaluation of the Stop TB Partnership. Described by IHSD as the “central jewel in the Partnership’s crown” of the Stop TB Partnership, the GDF was characterized as “developmentally sound” but “facing a serious short-term financing problem as well as a longer term funding challenge in supporting DOTS expansion programmes.” Subsequently, during this report period, additional financial resources were secured to cover the short term gap and the STB Partnership secretariat initiated the process of formulation of a suitable financial policy to underpin sound funding decisions by GDF.

Appendix One

Stop TB Partnership

Global TB Drug Facility

Statement Income and Expenditures

1 January – 31 December 2003

(all figures in US$,000)

|  | Notes |  | 2003 |
| --- | --- | --- | --- |
| Income |  |  |  |
| Government and their Agencies – Specified | 1 |  | 14,911 |
| Foundations and Others | 2 |  | 154 |
| In-kind contributions | 3 |  | 188 |
| Contributions allocated to GDF by Partnership Secretariat | 4 |  | 1,095 |
| Total Income |  |  | 16,348 |
| Expenditure |  |  |  |
| Drugs, including laboratory inspection, insurance, pre-shipment inspection and freight |  |  |  |  | 13,626 |
| Quality assurance and Pre-qualification |  |  | 144 |
| Technical Assistance and Monitoring |  |  | 1,255 |
| Advocacy and Communications |  |  | 21 |
| Indirect costs | 5 |  | 519 |
| Total Expenditure |  |  | 15,565 |
| Surplus of Income over Expenditure |  |  | 783 |

Stop TB Partnership

Global TB Drug Facility

Notes to the income and expenditure table

(all figures in US$,000)

| 1. Government and their Agencies - Specified |  |
| --- | --- |
| The total amount shown under this heading comprises: |  |
| CIDA | 8,530 |
| Japan | 46 |
| Norway | 748 |
| The Netherlands | 2,587 |
| USAID | 3,000 |
| Total | 14,911 |
| 2. Foundations and Others |  |
| The total amount shown under this heading comprises: |  |
| Procter and Gamble | 24 |
| University of Harvard Medical School | 130 |
| Total | 154 |
| 3. In-kind contributions |  |
| This comprises the services of seconded staff from Management Sciences for Health | 188 |
| 4. Contributions allocated to GDF by the Partnership Secretariat |  |
| During the year, the Secretariat allocated certain amounts to the GDF from the contributions it had itself received from various donors, the details of these are as under: |  |  |
| Open Society Institute | 250 |
| UK-DFID | 595 |
| World Bank | 250 |
| Total | 1,095 |
| 5. Indirect Costs |  |
| The amount of indirect costs shown under expenditure comprises Programme Support Costs (PSC) levied by WHO | 519 |

Appendix Two

Details of GDF Country Support Performance and Impact Indicators

Table 1: GDF Performance Indicators

| GDF Core Functions | Activity | Reporting period (July 1st to Dec 31st 2003) | Previous reporting period (Jan 1st to June 30th 2003) | Cumulative (Up to Dec 31st 2003) |
| --- | --- | --- | --- | --- |
| Funding | Total cash raised to date for GDF operations (in US$,000) | 15,886 | $275 | 39,328 |
|  | Total cash raised to date for GDF grants (in US$,000) (and % vs. target as per strategic plan – $224 million up to 2005) |  |  | 31,009 (16%) |
|  | Total financial shortfall to cover projected drug commitments (in US$,000) | 14,000 | 27,000 |  |
| Grant making | Total patients approved during reporting period via grants (and % vs. target as per strategic plan -11.8 million up to 2005) | 337,135 | 177,804 | 2.3 million (20% of strategic plan target) |
|  | Estimated value of commitments made (US$,000) | 10,168 | 4,253 | 57,300 |
| Direct Procurement | Number of applications approved for Direct Procurement | 9 | 2 | 11 |
|  | Total value of Direct Procurement Orders (in US$,000) | 4,700 | 1,322 | 6,022 |
|  | Total number of patients approved (including buffer) via direct procurement. | 88,665 | 383,316 | 471,981 |
| Applications and review | No. of HBC receiving GDF support (Grant or Direct Procurement) | 12 | 10 | 12 |
|  | TRC meetings completed vs. target as per workplan | 50% | 100% |  |
|  | No. of rounds of applications and review | 1 | 1 | 7 |
|  | No. of applications for GDF support | 12 | 14 | 81 |
|  | Number of applications approved for support | 8 | 11 | 58 |
|  | Applications rejected and not accepted thereafter | 2 | 1 | 6 |
|  | Applications accepted that were previously rejected or placed under consideration | 1 | 2 | 12 |
|  | Average time from receipt of application to grant agreement | 118 Days | 173 Days |  |
|  | Number of pre delivery country visits to GDF countries | 6 | 4 | 42 |
|  | Percentage of countries that have received formal feedback from GDF at review stage | 100% | 100% | 100% |
| Monitoring & Evaluation | Number of monitoring missions to GDF countries | 10 | 4 | 22 |
|  | Number of applications monitored for repeat support | 7 | 9 | 16 |
|  | No. of countries that have received formal feedback from GDF following monitoring mission | 10 | 4 | 22 |
|  | Number of applications accepted for repeat support (following desk audit) | 4 | 7 | 10 |
|  | % GDF countries receiving Technical Assistance (TA) for drug management/TA as part of GDF monitoring | 100% | 100% |  |
|  | % Monitoring missions on time | 71% | 50% |  |
| White List and supplier mobilisation | Number of companies on WHO white list | 4 | 0 | 4 |
|  | Number of companies applying to join white list | 17 | 17 | 17 |
|  | Number of companies, on WHO white list from high burden TB countries. | 4 | 0 | 4 |
| Procurement | Number of applicants which have received drug deliveries | 18 | 14 | 52 |
|  | Average lead time from placing order to receipt of drugs in country (excluding countries which asked for delayed deliveries) | 128Days | 145Days |  |
|  | No of countries (and percentage) receiving drugs within agreed lead time (5 months after GA signed by applicant) | 10 (55%) | 11 (79%) | 26 (50%) |
|  | Drug orders placed | 13 | 15 | 54 |
|  | Orders on-time | 57.4% | 13.6% |  |
|  | Orders complete | 97,8% | 81.8% |  |
|  | Orders error and damage free | 89.3% | 86.4% |  |
|  | Perfect order achievement | 50.1% | 9.6% |  |
|  | Average Time taken for GDF drugs to clear customs & registration (delivered at Central drug store) | 7 days | 19 days |  |

Table 2 GDF Impact Indicators

| Area | Indicator | Reporting period (July 1st to Dec 31st 2003) | Previous reporting period (Jan 1st to June 30th 2003) |
| --- | --- | --- | --- |
| Procurement | No countries which stocked out because GDF drugs did not arrive on time | 0 | 0 |
|  | No countries running on buffer stocks | 3 | 0 |
| Direct Procurement (Affordability) | Direct procurement price as a percentage of prices that GDF countries were buying at previously |  |  |
|  | RH 150+75 | GDF price is 44% lower |  |
|  | RHZE 150+75+400+275 | GDF price is 29% lower |  |
| Quality | % GDF drugs of known good quality | 100% | Unknown |
|  | % GDF batches that were rejected by pre shipment quality control | 0% | 0% |
|  | % GDF batches recalled in country i.e. failed in-country quality control | 0% | 0% |
| Drug management | % of GDF countries with stock out at national, intermediate or peripheral levels | 28% | 0% |
|  | % GDF countries with out of date drugs (non GDF drugs) | 14% | 50% |
|  | % GDF countries which followed up on at least 50% of drug management recommendations, as part of GDF monitoring | 67% | 75% |
| Standardization | No. of countries adopting WHO recommended treatment regimens after GDF support (if not using before) | 0 | 3 |
|  | No of countries using FDCs through GDF support | 8 | 12 |
|  | No of countries using 4FDC through GDF support | 10 | 10 |
|  | No. countries using blistered products with GDF support | 3 | 5 |
| DOTS Expansion | No. of countries which introduced DOTS or developed a DOT Expansion Plan due to GDF support | 2 | 3 |
| Cure Rates | Estimated number of TB patients that will be cured with GDF drugs | 286,565 | 151,133 |
| Drug Prices | GDF prices in comparison to World International price (per product) | GDF prices/Int’l Price |  |
|  | RH 150+75 | 1.35 / 2.15 |  |
|  | RHZE 150+75+400+275 | 3.51 / 5.41 |  |
|  | Average cost per additional cure in US dollars (including quality, insurance and shipping) | $15.5 | $15.5 |
|  | Price as a % of previous drug price that the country was buying at. |  |  |
|  | RH 150+100 | GDF price is 44% lower |  |
|  | RHZE 150+75+400+275 | GDF price is 29% lower |  |
| Political commitment/ additionally/ GDF Terms and Conditions | % countries which have complied with all GDF terms and conditions of support | 85% | 100% |
|  | % of countries which implemented recommendations from country visits or TRC | 83% | 100% |
|  | % of countries which maintained or increased Govt. expenditure on NTP post GDF support | 62% | 75% |

## Table 3– Details of GDF Country Support: July 1 – Dec. 31 2003 - TB cases and patient numbers in GDF supported countries and demand indicators

| #### A | B | C | D | E | F | G | H | I | J | K | L |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| #### Country | Estimated TB cases | Total patients to be treated with GDF drugs (not including buffer) | Total patients to be treated with GDF drugs (including buffer) | Estimated Total Value of grant including buffer (D*13.2) | Estimated value of grant not including buffer (C*13.2) | Estimated TB Cases to Cure (C*0.85) | Cost per additional cure in US dollars (F/G) | Indicator 1 APPLY TO REVIEW in days | Indicator 2 REVIEW TO APPROVAL in days | Indicator 3 APPROVAL TO GRANT in days | Indicator 4 GRANT TO ORDER in days |
| Algeria | 15,541 | 9,800 | 19,600 | 258,720 | 129,360 | 8,330 | 15.5 | 39 | NA | NA | NA |
| Angola | 27,120 | 25,000 | 50,000 | 660,000 | 330,000 | 21,250 | 15.5 | 19 | NA | NA | NA |
| Burkina Faso | 23,363 | 200 | 400 | 5,280 | 2,640 | 170 | 15.5 | 48 | NA | NA | NA |
| Cambodia | 84,252 | 2773 | 2773 | 36,606 | NA | NA | NA | 21 | 16 | NA | NA |
| Central African Republic | 12,806 | 2,341 | 2,341 | 30,901 | 30,901 | 1,990 | 15.5 | 131 | 95 | 39 | NA |
| Equatorial Guinea | 909 | 660 | 1,320 | 17,424 | 8,712 | 561 | 15.5 | 36 | 16 | 67 | NA |
| Syria | 12,249 | 500 | 1,000 | 13,200 | 6,600 | 425 | 15.5 | 28 | NA | NA | NA |
| Turkmenistan | 4,072 | 3,025 | 6,050 | 79,860 | 39,930 | 2,571 | 15.5 | 33 | 16 | NA | NA |
| Niger | 20,451 | 9,200 | 18,400 | 242,880 | 121,440 | 7,820 | 15.5 | 68 | 16 | 35 | NA |
| Madagascar | 41,236 | 25,400 | 50,800 | 670,560 | 335,280 | 21,590 | 15.5 | 202 | 16 | 34 | 18 |
| TFYR Macedonia | 718 | 706 | 904 | 11,933 | 9,319 | 600 | 15.5 | 14 | 204 | 34 | 19 |
| Zambia | 69,549 | 51,500 | 103,000 | 1,359,600 | 679,800 | 43,775 | 15.5 | 47 | 16 | NA | NA |
| Monitoring |  |  |  |  |  |  |  |  |  |  |  |
| Nigeria | 274,972 | 37,235 | 74,470 | 983,004 | 491,502 | 31,650 | 15.5 | 69 | 16 | 35 | 20 |
| Somalia | 32,270 | 11,000 | 11,000 | 145,200 | 145,200 | 9,350 | 15.5 | 62 | 14 | 224 | 34 |
| Sudan | 59,897 | 12,000 | 12,000 | 158,400 | 158,400 | 10,200 | 15.5 | 250 | 16 | 41 | NA |
| Togo | 7,345 | 1,654 | 2,481 | 32,749 | 21,833 | 1,406 | 15.5 | 62 | 16 | 35 | 20 |

## Table 4 -  Details of GDF Country Support: Cumulative (up to December 2003) - Supply statistics and supply indicators in GDF supported countries to date.

| Country | Date Applied to GDF | Date Reviewed by TRC | Date Grant Agreement sent | Date order placed | Date drugs arrived in country | Time taken to clear customs & registration | Indicator 1 APPLY to GRANT in days | Indicator 2 GRANT to ORDER in days | Indicator 3 ORDER TO ARRIVAL in days | Date monitoring mission needed for next year |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Algeria | 9 Aug 03 | 17 Sep 03 | NA | OTP | NA | NA | NA | NA | NA | NA |
| Angola (E4) | 8 Jul 02 | 24 Jul 02 | 6-Nov-02 | 4-Dec-02 | 7-May-03 | 1 | 121 | 28 | 154 | 2-Jan-04 |
| Angola | 29 Aug 03 | 17 Sep 03 | NA | OTP | NA | NA | NA | NA | NA | NA |
| Armenia (E3) | 14 Mar 02 | 23 Apr 02 | 1-Jul-02 | 20-Sep-02 | 11-Jan-03 | 19 | 109 | 81 | 113 | 8-Sep-03 |
| Azerbaijan | 24 Aug 02 | 30 Oct 02 | 18-Dec-02 | 17-Jan-03 | 16-Jun-03 | 51 | 116 | 30 | 150 | 11-Feb-04 |
| Bangladesh | 11 Mar 02 | 23 Apr 02 | 10-Jul-02 | 7-Aug-02 | 2-Jan-03 | 19 | 121 | 28 | 148 | 30-Aug-03 |
| Benin | 26 Sep 02 | 13 Mar 03 | 9 Oct 03 | 05 Nov 03 | NA | NA | 378 | 27 | NA | NA |
| Bosnia and Herzegovina | 7 Aug 02 | 13 Mar 03 | 12-May-03 | 16-Jun-03 | 3 Oct 03 | 7 | 302 | 11 | 109 | June 04 |
| Burkina Faso | 31 Jul 03 | 17 Sep 03 | NA | OTP | NA | NA | NA | NA | NA | NA |
| Burundi | 8 Jul 02 | 24 Jul 02 | 20-Dec-02 | 17-Jan-03 | 11-Jun-03 | 16 | 165 | 28 | 145 | 06-Feb-04 |
| Cameroon | 26 Sep 02 | 30 Oct 02 | 4 Jul 03 | 17 Jul 03 | 10 Oct 03 | NA | 281 | 13 | 85 | June 04 |
| Cambodia | 27 Aug 03 | 17 Sep 03 | - | 24 Nov 03 | na | NA | - | - | NA | NA |
| Central African Republic (E3) | 3 Apr 02 | 23 Apr 02 | 10-Jul-02 | 16-Jul-02 | 31-Dec-02 | 3 | 98 | 6 | 168 | 28-Aug-03 |
| Central African Republic (E6) | 19 Feb 03 | 30 Jun 03 | 11 Nov 03 | OTP | NA | NA | NA | NA | NA | NA |
| Congo (E2) | 14 Mar 01 | 25 Jul 01 | 30 Aug 01 | 11 Sep 01 | 14 Jan 02 | 18 | 169 | 12 | 125 | NA |
| Congo (A3) | 16 Apr 02 | 23 Apr 02 | 30-Aug-02 | 30-Aug-03 | 20-Jan-03 | 18 | 136 | 0 | 143 | 17-Sep-03 |
| Côte d'Ivoire (E4) | 8 Jul 02 | 24 Jul 02 | 6-Mar-03 | 25-Mar-03 | 30-Jun-03 | 59 | 241 | 19 | 97 | March 04 |
| Côte d'Ivoire (E6) | 22 Jan 03 | 13 Mar 03 | 16 Jun 03 | 02-Jul-03 | 9 Nov 03 | NA | 149 | 16 | 130 | March 04 |
| DPR Korea 1 year | 13 Jul 01 | 25 Jul 01 | 12 Oct 01 | 26 Oct 01 | 15 Nov 01 | 4 | 91 | 14 | 20 | 17 Aug 02 |
| DPR Korea 2 year | 8 Sep 02 | 30 Oct 02 | 14-Jan-03 | 7-Feb-03 | 3 Jul 03 | 4 | 128 | 24 | 146 | March 04 |
| DR Congo 1 year | 16 Jul 01 | 25 Jul 01 | 27 Nov 01 | 05 Dec 01 | 18 May 02 | NA | 134 | 8 | 164 | 9 Nov 02 |

| Country | Date Applied to GDF | Date Reviewed by TRC | Date Grant Agreement sent | Date order placed | Date drugs arrived in country | Time taken to clear customs & registration | Indicator 1 APPLY to GRANT in days | Indicator 2 GRANT to ORDER in days | Indicator 3 ORDER TO ARRIVAL in days | Date monitoring mission needed for next year |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| DR Congo 2 year | 10 Jan 03 | 13 Mar 03 | 13 Jun 03 | 20 Jun 03 | 9 Sep 03 | 3 | 154 | 7 | 81 | May 04 |
| Djibouti 1 year | 27 Mar 01 | 25 Jul 01 | 6 Dec 01 | 15 Jan 02 | 25 Apr 02 | 14 | 254 | 40 | 100 | 24 Oct 02 |
| Djibouti 2 year | 10 Jan 03 | 13 Mar 03 | 13 Jun 03 | 7 Jul 03 | 24 Aug 03 | NA | 154 | 20 | 48 | Feb 04 |
| Egypt | 3 Mar 03 | 13 Mar 03 | 9 Oct 03 | 14 Nov 03 | NA | NA | 220 | 36 | NA | NA |
| Eritrea | 13 Mar 02 | 13 Mar 03 | 7 Nov 03 | OTP | NA | NA | 664 | NA | NA | NA |
| Equatorial Guinea | 12 Aug 03 | 17 Sep 03 | 9 Dec 03 | OTP | NA | NA | NA | NA | NA | NA |
| Gambia | 4 Mar 03 | 23 Apr 03 | 25-Nov-02 | 4-Dec-02 | 15-May-03 | 0 | 266 | 9 | 162 | 10-Jan-04 |
| Haiti | 3 Jul 02 | 24 Jul 02 | 24-Jan-03 | 27-Jan-03 | 25-Jun-03 | 34 | 192 | 11 | 149 | 20-Feb-04 |
| India | 13 Jul 01 | 25 Jul 01 | 27-Sep-02 | 31-0ct-02 | 15-Jun-03 | 25 | 441 | 34 | 227 | 10-Feb-04 |
| India (2 year) | 11 Sep 03 | 12 Nov 03 | NA | NA | NA | NA | NA | NA | NA | NA |
| Indonesia | 18 Apr 02 | 23 Apr 02 | 8-Nov-02 | 15-Nov-02 | 28-May-03 | 37 | 204 | 7 | 194 | Jan 04 |
| Kenya 1 year | 19 Feb 01 | 14 Mar 01 | 29 Jun 01 | 08 Aug 01 | 20 Feb 02 | 6 | 130 | 40 | 196 | 2 Sep 02 |
| Kenya 2 year | 8 Sep 02 | 30 Oct 02 | 18-Dec-02 | 7-Feb-03 | 13-Jun-03 | 5 | 101 | 51 | 126 | Feb 04 |
| Kosova | 16 Oct 02 | 30 Oct 02 | 26-Mar-02 | 7-Apr-03 | 25 Jul 03 | 0 | 161 | 12 | 109 | Mar 04 |
| Liberia | 25 Jan 01 | 25 Jul 01 | 6-Dec-01 | 11-Feb-02 | 3-Oct-02 | 17 | 315 | 67 | 234 | NA |
| Madagascar | 27 Feb 03 | 17 Sep 03 | 6 Nov 03 | 24 Nov 03 | NA | NA | 252 | 18 | NA | NA |
| Mali | 19 Sep 02 | 13 Mar 03 | 13 Jun 03 | 02 Jul 03 | 7 Nov 03 | NA | 267 | 19 | 128 | Jul 04 |
| Mauritania | 15 Apr 02 | 23 Apr 02 | 19-Aug-02 | 4-Oct-02 | 1-Feb-03 | NA | 126 | 46 | 120 | Dec 03 |
| Moldova 1 year | 27 Feb 01 | 14 Mar 01 | 27 Jun 01 | 05 Jul 01 | 15 Oct 01 | 21 | 120 | 8 | 102 | 14 Aug 02 |
| Moldova 2 year | 20 Jul 02 | 24 Jul 02 | 24 Oct 02 | 20 Nov 02 | 19 May 03 | 1 | 96 | 27 | 180 | Jan 04 |
| Myanmar 1 year | 26 Feb 01 | 14 Mar 01 | 28 Jun 01 | 08 Aug 01 | 24 Mar 02 | 33 | 122 | 41 | 228 | 19 Aug 02 |
| Myanmar 2 year | 8 Sep 02 | 30 Oct 02 | 14 May 03 | 29 May 03 | 9 Sep 03 | NA | 248 | 15 | 103 | April 04 |
| Niger (E3) | 22 Apr 02 | 30 May 02 | 10-Jul-02 | 6-Sep-02 | 27-Jan-03 | NA | 79 | 58 | 143 | Nov 03 |
| Niger | 11 Jul 03 | 17 Sep 03 | 7 Oct 03 | OTP | NA | NA | 119 | NA | NA | NA |
| Nigeria (1year) | 28 May 01 | 25 Jul 01 | 23-Nov-01 | 21-Dec-01 | 22-Oct-02 | NA | 179 | 28 | 305 | NA |
| Nigeria (2year) | 10 Jul 03 | 17 Sep 03 | 7 Nov 03 | 27 Nov 03 | NA | NA | 120 | 20 | NA | NA |
| Orissa State | 7 Mar 02 | 23 Apr 02 | 12-Aug-02 | 31-Oct-02 | 7 June 03 | NA | 158 | 80 | 219 | NA |

| Country | Date Applied to GDF | Date Reviewed by TRC | Date Grant Agreement sent | Date order placed | Date drugs arrived in country | Time taken to clear customs & registration | Indicator 1 APPLY to GRANT in days | Indicator 2 GRANT to ORDER in days | Indicator 3 ORDER TO ARRIVAL in days | Date monitoring mission needed for next year |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Pakistan | 12 Jul 01 | 25 Jul 01 | 15-Nov-01 | 30-Jan-02 | 20-Dec-02 | 18 | 126 | 76 | 324 | 17-Aug-03 |
| Philippines | 22 Jul 02 | 24 Jul 02 | 29-Nov-02 | 20-Jan-03 | 3 Aug 03 | 8 | 130 | 52 | 195 | Dec 03 |
| Philippines PPP | 22 Jul 02 | 24 Jul 02 | 25-Nov-02 | 20-Jan-03 | 22-Jun-03 | 15 | 126 | 56 | 153 | Dec 03 |
| Rwanda | 21 Oct 02 | 30 Oct 02 | 17-Dec-02 | 7 Apr 03 | 17 Oct 03 | NA | 57 | 111 | 193 | May 04 |
| Sierra Leone | 16 Jul 01 | 25 Jul 01 | 16-Dec-02 | 5-Feb-03 | 4 Sep 03 | 15 | 518 | 51 | 211 | May 04 |
| Somalia 1 year | 28 Feb 01 | 14 Mar 01 | 28 Jun 01 | 08 Aug 01 | 09 Jun 02 | 1 | 120 | 41 | 305 | 13 Dec 02 |
| Somalia 2 year | 10 Jan 03 | 13 Mar 03 | 6 Nov 03 | 10 Dec 03 | NA | NA | 300 | 34 | NA | NA |
| Sudan 1 year | 16 Jul 01 | 25 Jul 01 | 12 Nov 01 | 07 Dec 01 | 24 Apr 02 | 1 | 119 | 25 | 138 | 18 Jan 03 |
| Sudan 2 year | 10 Jan 03 | 17 Sep 03 | 13 Nov 03 | OTP | NA | NA | 307 | NA | NA | NA |
| Syria | 20 Aug 03 | 17 Sep 03 | NA | OTP | NA | NA | NA | NA | NA | NA |
| Tajikistan 1 year | 26 Feb 01 | 14 Mar 01 | 28 Jun 01 | 08 Aug 01 | 23 Feb 02 | 3 | 122 | 41 | 199 | 24 Nov 02 |
| Tajikistan 2 year | 10 Jan 03 | 13 Mar 03 | 13 Jun 03 | 7 Jul 03 | 7 Sep 03 | 8 | 154 | 24 | 62 | May 04 |
| Togo 1 year | 25 Jan 01 | 25 Jul 01 | 14-Nov-01 | 21-Dec-01 | 3-Sep-02 | 6 | 293 | 37 | 256 | 21-Jun-03 |
| Togo 2 year | 17 Jul 03 | 17 Sep 03 | 7 Nov 03 | 27 Nov 03 | NA | NA | 113 | 20 | NA | NA |
| TFYR Macedonia | 27 Feb 03 | 13 Mar 03 | 6 Nov 03 | OTP | NA | NA | 252 | NA | NA | NA |
| Turkmenistan | 15 Aug 03 | 17 Sep 03 | NA | OTP | NA | NA | NA | NA | NA | NA |
| Uganda | 18 May 01 | 25 Jul 01 | 14-Nov-01 | 21-Dec-01 | 8-Dec-02 | 6 | 180 | 37 | 352 | 5-Aug-03 |
| Uzbekistan | 5 Apr 02 | 23 Apr 02 | 11-Dec-02 | 5-Feb-03 | 18 Aug 03 | NA | 250 | 56 | 194 | Apr 04 |
| Yemen Emergency | 13 Jul 01 | 25 Jul 01 | 11 Sep 01 | 11 Sep 01 | 09 Mar 02 | 62 | 60 | 0 | 179 | 18 Jan 03 |
| Yemen Regular | 10 Feb 03 | 13 Mar 03 | 9 Oct 03 | OTP | NA | NA | 241 days | NA | NA | NA |
| Zambia (E3) | 15 Apr 02 | 23 Apr 02 | 12-Jul-02 | 16-Jul-02 | 30-Dec-02 | 8 | 88 days | 4 days | 167 days | 27-Aug-03 |
| Zambia | 1 Aug 03 | 17 Sep 03 | NA | OTP | NA | NA | NA | NA | NA | NA |

NA = Information not available.

OTP = Order to be placed next period following receipt of grant agreement letter from country

Table 5 – Key Indicators for the GDF Monitoring Countries (data taken from the GDF monitoring checklist reports or GDF desk audit report)

| #### Country | Case management |  | Adherence to all GDF terms + Conditions of support | Evidence of Follow up from recommendation of Previous Visit + TRC | Financial Management |  | Drug Management | Approved for 2nd year |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | % DOTS coverage before GDF | % DOTS coverage with GDF |  |  | Govt. TB expenditure prior to GDF support | Govt. TB expenditure after GDF support |  |  |
| Moldova | 0 | 32 | Yes | Yes | No data | $1,145,131 | TB drugs are mostly managed well. In two non-DOTS districts, shortages of TB drugs in 2002. | Yes |
| Myanmar | 77 | 84 | Yes | Yes | $212,000 | $790,833 | The NTP has increased availability of drugs, though need education of patients, training of staff and additional expertise. | Yes |
| DPR Korea | 33 | 45 | Yes | Yes | $450.000 | $572,060 | Problems in recording accurate stock balances. Distribution of drugs does not follow in accordance with the orders submitted. The monthly and bi- monthly order cycles considered more efficient and should be used. | Yes |
| Kenya | 100 | 100 | Yes | Yes | $6,297,456 | $6,193,250 | NLTP should develop tools to verify drug distribution with expected drug consumption based on patient data. PTLCs should verify the actual physical stock in provincial stores with the stock recorded in the store registers prior to submitting their bi-annual stock reports to the central level. | Yes |

| #### Country | Case management |  | Adherence to all GDF terms + Conditions of support | Evidence of Follow up from recommendation of Previous Visit + TRC | Financial Management |  | Drug management | Approved for 2nd year |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | % DOTS coverage before GDF | % DOTS coverage with GDF |  |  | Govt. TB expenditure prior to GDF support | Govt. TB expenditure after GDF support |  |  |
| Djibouti | 100 | 100 | Yes | Yes | $1,065,000 | $795,000 | Well managed by PNLAT. Due to a lack of store reports from inside Djibouti, the flow and consumption of drugs cannot be judged. | Yes |
| Somalia | 73 | 100 | Yes | Yes | No data | $289,408 | Well managed by WHO SOM Office/ 14 NGO’s. Due to a lack of store reports from inside Somalia, the flow and consumption of drugs cannot be judged. | Yes |
| Sudan | 80 | 97 | Yes (however many NA in dossier) | Yes (however many NA in dossier) | No data | $785,204 | TB drugs are mostly managed well weaknesses in the distribution routines from Central Medical Store to the states. | Placed under consideration and eventually accepted. |
| Tajikistan | 0 | 10 | Yes | Yes | $34,475 | $40,552 | GDF drugs are properly managed. A new drug management system will be implemented. | Yes |
| Bangladesh | 92 | 98 | Yes | Yes | $403,034 | $4,275,533 | Drug management training has been carried out and a system for drug distribution is in place. Stockout at the central store reported | Yes |
| Country | Case management |  | Adherence to all GDF terms + Conditions of support | Evidence of Follow up from recommendation of Previous Visit + TRC | Financial Management |  | Drug management | Approved for 2nd year |
|  | % DOTS coverage before GDF | % DOTS coverage with GDF |  |  | Govt TB expenditure prior to GDF support | Govt TB expenditure after GDF support |  |  |
| India | 30 | 67 | Yes | Yes | $19,870,000 | $18,720,000 | Drug supply process runs smoothly. Good understanding of drug management system. | Yes |
| Pakistan | 12 | 45 | Yes | Yes | $7,231,000 | $10,078,500 | No permanent or sufficient drug storage facility. Drug supply mostly ad hoc. Good stock record keeping | Pending |
| Philippines | 90 | 100 | Yes | Yes | $2,464,000 | $2,664,000 | Ensured uninterrupted supply of anti-TB drugs, Drug stock record keeping not satisfactory | Yes |
| Congo-Brazzavile | 100% | 100% | No | Yes | None (only salaries) | None (only salaries) | Distribution problems. Situation in periphery not known. Over-consumption of drugs suspected. | Pending |
| Gambia | 87% | 100% | Yes | Yes | $19,100 | $13,933 | Drug distribution should be integrated within the national drug distribution system | Pending |
| Niger | No reliable data | No reliable data | No | No | None | None | Drug management and monitoring weak at the central level and in most of the regions | Pending |
| Uganda | 100% | 100% | Yes (however it is unclear whether the Government did take full responsibility for import duties and taxes | Yes | $430,783 | $41,667 | Lack of human capacity is limiting proper drug management. Limited information on stocking. Good central NTP drug store. Poor communication/Co-ordination between central NTP drug store and National medical store. | Pending |

END NOTES TO APPENDIX 2

Covers new money actually received by the trust fund or WHO, during the reporting period.  The figure does not include expected contributions.

Includes a projected shortfall for all three years of a grant. Projections are based on purchase orders Projected contributions from USAID, Netherlands and CIDA for 2004 have been included.

Covers patients approved by the TRC and STB Coordinating Board during the report period [new applications and monitoring applications] but no forward projection of patient numbers for 2nd or 3rd year.  Patient numbers are taken from Table Three, Appendix 3, and are derived from grant agreements or GDF application forms.

Estimated value of commitment includes a forward projection for all three years of  a multi-year grant including a projection for the 2nd and 3rd year where relevant. The value is derived from grant forecasts based on a value of $13.2 per patient, as per Table 3, Appendix 3.  This shows the liabilities the CB will build up, should all three years of a grant be provided and should the patient numbers not diverge dramatically from those approved in the first year.

This commitment is based on the value of $13.2 per patient only where more realistic estimations are not available. More realistic estimations are derived from the actual purchase order and estimations are refined as the 2nd year or 3rd year grant is signed.

Based on PO or based on order agreement forecast, where no PO exists.

TRC meetings are scheduled to be held three times a year.  In 2003, the TRC  met in March and September.  These percentage figures were made compared with 2002 schedule - April/July/October in 2002.

A country that applies, is not approved and reapplies is considered as one country but two applications. A country that applies for emergency support and regular support is also considered as one country, but two applications. A second year of support [i.e. monitored] is not considered as a new application.

Not including countries that were under-consideration and decision pending through the previous TRC.

All countries which are accepted or placed under consideration for a 3 year grant receive a GDF country visit. Emergency countries receive country visits at the discretion of the TRC. Direct Procurement countries do not receive country visits.

All countries receive formal feedback in the form of a letter and email detailing the TRC recommendations. All countries that receive a country visit are sent a copy of the GDF country visit report.

All countries receiving 3 year grants receive monitoring missions. All direct procurement countries receive monitoring missions. Emergency countries receive monitoring missions if they reapply for GDF support (additional grant or direct procurement).

Number of countries which went to desk audit during this report period.

Every GDF monitoring mission supplied the country with feedback.

During this reporting period, Togo (2nd year), Nigeria (2nd year), Sudan (2nd  year) and India (2nd year) were accepted for repeat support.

Monitoring mission on time means it happens 6-8 months after drug delivery, as per GDF standard operating procedures.

The list has been developed as a result of the Procurement, Quality and Sourcing Project: Access to Anti-Tuberculosis Drugs of Acceptable Quality, which was initiated in 2002 by the GDF Secretariat in conjunction with WHO Department for Essential Drugs and Medicines Policy/Quality Assurance and Safety: Medicines (EDM/QSM).

While over 70 manufacturers have expressed an interest in being pre-qualified, at present, 17 manufacturers have actually submitted dossiers for evaluation and made tentative arrangements for site inspections.

A split order is considered as one delivery.

After grant signature, the agreed lead time in 5 months.  However some countries may request a longer lead time.

The "perfect order" indicator measures the completeness, quality and timeliness of the orders.

The perfect order is a logistics management tool based on:

- On-time delivery

- Order completeness

- Freedom from error and damage

Perfect order achievement = % on-time x % complete x % error free of all orders.

Data gathered form monitoring check list and desk audit reports. Note while Bangladesh did stock out of drugs at the central store, this is not because the GDF drugs did not arrive on time.

Source:  MSH Drug price indicator guide www.msh.org. The data as of 2003.

The MSH price is for RH 150/100

Data from the monitoring checklist.

“Known good quality” is defined as drugs produced by manufacturers under the oversight of a competent regulatory authority or approved by WHO.

Data from monitoring checklist.

Two out of seven monitoring checklist reports reported stock outs.

One out of seven monitoring checklist reports reported stock outs. Note this does not refer to GDF drugs.

Recommendations from the TRC, previous country mission or monitoring mission are supposed to be followed up by the country before the next monitoring mission.

Based on the countries that were reviewed by TRC and approved by CB during this report period.  As of  December, 8 countries in 7th TRC and 12 countries in 6th TRC.

Some countries apply to the GDF in order to start DOTS. This data is derived form the application form.

Covers patients approved by the TRC and STB Coordinating Board during the report period [new applications and monitoring applications] but no forward projection of patient numbers for 2nd or 3rd year.  Patient numbers are taken from Table Three, Appendix 3, and are derived from grant agreements or GDF application forms. The figure assumes that 85% of total patients to be treated with GDF drugs will be cured. The figure is derived from the estimated cure rate of 85 % - the official global target for TB control. Covers patients approved by TRC and CB during report period.

Note the MSH  price is for RH 150/100.

Cost per estimated patient cured, excluding buffer figure comes from the Secretariat estimation of $13.2 per patient drug cost and based on a 85% cure rate.

Sources from MSH price indicator guide. The data was reported in 2003.

Data is from monitoring checklist

One country did not comply with all GDF terms and conditions of support in this report period. See Table 5, Appendix Three for more information.

End notes for Table 4  Appendix 3:  Details of GDF Country Support: July 1 – Dec 31 2003 - TB cases and patient numbers in GDF supported countries and demand indicators:

? The table provides information on countries and NGO’s approved for support during this report period (July 1 – Dec 31 2003).

WHO TB Estimates 2003 from WHO REPORT 2003.

Figures are taken from the country grant agreement letter and from the application form. The figures correspond to the number of patients provided with GDF drugs.

Figure is taken from the country grant agreement letter and corresponds to the number of patients supplied with GDF drugs multiplied by two for those countries receiving buffer.

Cost of drugs, insurance, and freight. No figure includes cost of batch testing and pre-shipment inspection. For the figures an average value of 13.2 has been used to reflect the average cost to treat a patient, a figure derived from averaging the total grant value for those countries for which a regular grant order has been placed.

85% of total patients to be treated with GDF drugs (not including buffer). The figure is derived from the estimated cure rate of 85 % - the official global target for TB control.

Cost per estimated patient cured, excluding buffer.

Time taken from receipt of application in the Secretariat to when it was reviewed by the Technical Review Committee.

Time taken from review by Technical Review Committee to approval  by the Stop TB Co-ordinating Board.

Time taken from approval by the Stop TB Coordinating Board to grant agreement being sent.

Time taken from grant agreement being sent to order placed by GDF.

Time taken from receipt of application in the Secretariat to grant agreement being sent.

Time taken from grant agreement being sent to grantee to Secretariat for placing order.

Time taken from order being placed to TB drugs arriving in the country.

Date of the monitoring mission required for a further year of GDF support. This date is estimated in accordance with the situation of the country and the availability of a suitable team to undertake the mission.

Time taken from receipt of application in the Secretariat to grant agreement being sent.

Time taken from grant agreement being sent to grantee to Secretariat for placing order.

Time taken from order being placed to TB drugs arriving in the country.

Date of the monitoring mission required for a further year of GDF support. This date is estimated in accordance with the situation of the country and the availability of a suitable team to undertake the mission.

Time taken from receipt of application in the Secretariat to grant agreement being sent.

Time taken from grant agreement being sent to grantee to Secretariat for placing order.

Time taken from order being placed to TB drugs arriving in the country.

Date of the monitoring mission required for a further year of GDF support. This date is estimated in accordance with the situation of the country and the availability of a suitable team to undertake the mission.

The regular expenditure of WHO for DPR Korea NTP in 2000/2001. The government of DPR Korea provides adequate human resources (around 5000 dedicated TB staff) and physical infrastructure for effective implementation of the DOTS programme. However, commitment cannot be presented as a financial figure due to the inconvertible nature of the DPRK currency (Korean Won). From Desk Audit & Monitoring Report Sep. 2002.

TB expenditure from Donors (GFATM & WHO) and GDF grants. Information on budgets of 14 NGO’S, executing the DOTS strategy in Somalia, is not available. No TB budget from Somalia government.

NA: Information not available.