## Slide 1: Elements in each WG strategic plan
element | DOTS expans | DOTS-Plus | TB/HIV | drugs | diagnost | vaccines | ACSM
Strategic vision | + | + | + | + | + | + | +
Objs | + | + | + | + | + | + | +
Targets | +/- | + | - | + | + | + | +
Activities | + | + | +/- | + | + | + | +
Timelines | + | + | - | + | + | + | +
Impact | + | + | - | - | - | No vaccine by 2015 | +/-
Activities budgeted | +/- | + | - | - | + | + | +
Funding | - | - | - | - | _ | + | +/-
Risks | - | + | + | + | + | + | -

## Slide 2: Revised Global Plan 2006-2015 timetable
Date | Milestone
2 May | Steering Group meeting
4 May | Coordinating Board consideration
end May | Finalised WG plans and regional scenarios
June-July | Drafting of 1st full Global Plan
Aug-September | Wide consultation and review
end September | Finalised Global Plan
Oct-December | Production of Global Plan (editing, design, translation, printing etc)
January 2006 | Launch, Davos (to be confirmed)