## Slide 1: Innovation in case finding for tuberculosis: The FIDELIS Initiative
Nils E. Billo MD, MPH
Executive Director, International Union Against Tuberculosis and Lung Disease (The Union)
Stop TB Partnership Coordinating Board meeting
Addis Ababa, Ethiopia 3-4 May 2005

## Slide 2: Outline
Review rationale behind FIDELIS
Main principles of FIDELIS
Update on project implementation
Results to date
    FIDELIS outcome measure
    Overall and individual project results
Future direction

## Slide 3: Why FIDELIS ?
Despite global efforts, DOTS case detection rate remains below global target (70%)
    2001 - 32%
    2002 - 37%
    2003 - 45%
Need to explore alternative means to rapidly increase detection of new smear positive cases while maintaining high cure rates
Notes: I realize that this group is well aware of the rationale behind FIDELIS but a few words on CDR may be reasonable

## Slide 4: FIDELIS principles
Small projects of one-year duration (USD 150K-250K)
Local solutions to local problems
Encourage innovative ideas within existing programs
Focus on populations with limited access
Systematic monitoring and evaluation

## Slide 5: Project implementation update
32 phase I contracts negotiated or completing negotiations
13 countries with at least one FIDELIS project
    15 of 32 projects in China or Pakistan
    24 of 32 in World’s six highest burden countries
7 of 15 eligible phase I projects approved for phase II activities
Notes: Some of these data have not changed as we have not had another round of phase I applications since last summer
I would again highlight that almost half of projects are in China or Pakistan and that two thirds are in the world’s six highest burden countries
What is probably new is that we now have several successful phase I approaches scaling up which is of interest to CIDA
By eligible, I mean that 15 projects have completed or are nearing completion or their phase I activities and could have applied for phase II

## Slide 6: FIDELIS results
Main outcome measure
    Cost per additional weighted treatment success (AWTS) – target less than $80 USD
    Difference between the number of weighted treatment successes during the project and during the same months of the previous year
    Weighting based on proportion of new cases registered that are designated as having ‘limited access’ to care
Notes: The group may not be familiar with the details of the outcome measure and its calculation – you may choose not to use this
You could also highlight both the weighting (0.5 for non limited access to 1.0 for limited access) and the designation process (scoring system until now using both symptom duration and care seeking behavior soon to be simplified to total treatment delay of 12 weeks or greater = LA)

## Slide 7: FIDELIS results (to end 4th quarter, 2004)
Cost per AWTS projections available for 21 of 32 phase I projects
8 of 21 projects have a projected cost per AWTS lower $80 USD
5 projects have projected costs per AWTS between $80 and $150 USD
Few projects with high cost per AWTS projections (e.g. $2318 USD)
Notes: An initial slide with overall results to the end of the 4th quarter, 2004 (1st quarter 2005 to be available the end of May)
Main message is that 13 of 21 reporting projects are below or within reach of USD $80 per AWTS target
On the other hand, some projects have surprisingly high cost per AWTS projections

## Slide 8: FIDELIS (project-specific results)
Enhancing diagnostic services in urban slums in Africa
Notes: I have selected five individual projects to present for their different approaches and results
For each project, there is a graph that shows the case finding data to date in relation to the project target and baseline with a projected cost per AWTS
This first project is interesting in that it did not find the additional cases that most would expect in such a densely population, poor area (Kibera slums, Nairobi)
I would highlight the value in such projects – can provide as much information as projects that exceed their targets – need to explore why they have not found the expected cases - ?estimates inaccurate ?accessibility was not a big issue for population so new, local centres did not affect case finding ?other

## Slide 9
Notes: As there are five slides like this – it may be helpful to orient the audience – these are cumulative NSP cases over the 12 month project duration in the project sites, the projected cost per AWTS is based on case finding data in relation to previous year, the proportion of cases that are LA in the project, the projected treatment success rate and the budget is the pro-rated project budget for the duration of activities assessed
The white diamond is last years’ NSP cases detected during the same month, the pink square is the target for the project and the yellow triangle is the achieved to date
Note that the target is set by the project – some may be much higher than needed to reach $80 per AWTS goal

## Slide 10: FIDELIS (project-specific results)
Enhancing diagnostic services in urban slums in Africa
Mobilizing junior high school students in Anhui, China to screen family members for tuberculosis
Notes: Interesting project in its innovative approach – really what FIDELIS is all about – teaches junior high students about tuberculosis – gives them project card with space for mother, father, siblings etc. with check box for symptoms compatible with tuberculosis; cards are brought back to school and symptomatic families are followed up by village doctor

## Slide 11
Notes: Project on track to reach $80 per AWTS even if below target figures to date

## Slide 12: FIDELIS (project-specific results)
Enhancing diagnostic services in urban slums in Africa
Mobilizing junior high school students in Anhui, China to screen family members for tuberculosis
Strengthening referrals from county hospitals to county tuberculosis dispensaries in Hunan, China
Notes: One of the early successful China projects – more of a health system intervention that a ‘community’ approach

## Slide 13
Notes: Again, targets were very high - so project achieved lower cost per AWTS than all other projects, even though short of target
I would highlight that the approach has been adopted by the National Government – which is really the purpose of FIDELIS to be an ‘innovation mechanism’ not a ‘development mechanism’ – i.e. if something works it should be picked up by NTP or other funding mechanism e.g. GFATM

## Slide 14: FIDELIS (project-specific results)
Enhancing diagnostic services in urban slums in Africa
Mobilizing junior high school students in Anhui, China to screen family members for tuberculosis
Strengthening referrals from county hospitals to county tuberculosis dispensaries in Hunan, China
Training and utilizing community volunteers to increase community awareness in North Sumatra
Notes: 500 or so community volunteers (teachers, salespeople, computer programmers) trained to increase awareness and identify suspects in their community and support them through treatment

## Slide 15
Notes: Successful to date – even though the project is close to target, the cost per AWTS is still higher than $80 as the targets were less ambitious –however, some previously delayed reporting and reduced expenditures have since put the project very close or below the $80 goal

## Slide 16: FIDELIS (project-specific results)
Enhancing diagnostic services in urban slums in Africa
Mobilizing junior high school students in Anhui, China to screen family members for tuberculosis
Strengthening referrals from county hospitals to county tuberculosis dispensaries in Hunan, China
Training and utilizing community volunteers to increase community awareness in North Sumatra
Orienting and linking private practitioners to tuberculosis control activities in Jogjakarta and Bali
Notes: Again, it is interesting to see what works within the FIDELIS initiative as well as what does not appear to find additional cases in such a short time frame
This project from Indonesia attempted to link private practitioners into the government system to increase referrals and reporting of cases

## Slide 17
Notes: As evident here, almost no additional cases have been detected in the districts implementing the approach. Even where there has been identification of suspects by PPs, there has been significant loss to follow up before they reach the diagnostic centres
It also highlights the geographic-specific nature of some project findings – just because something is cost effective and works great in India (as reported by the PPM group) does not mean that it is cost effective or will work everywhere
This does not mean the we should abandon PPM approach but to look carefully at what components work and why
(as an aside Nils, this was an academically strong, motivated group that followed things carefully and I think the results are credible – though the PPM crowd may not like to hear this)

## Slide 18: FIDELIS (other findings)
Rapid implementation and short time frame for activities a challenge for many sites
Documenting limited access increases workload but provides valuable information for project and program
Routine ‘patient stories’ provide important qualitative perspective to tuberculosis project and program delivery
Notes: The quick time frame for projects from contract signing to project start date is a big challenge for many projects, especially government contractors that may not have the additional staff to carry out activities
I also would highlight that capturing limited access is valuable for the projects/programs to collect but it is clearly an additional workload
I also think our approach during monitoring FIDELIS projects of visiting individual patients on a routine basis provides valuable information on FIDELIS projects and the tuberculosis control services in general

## Slide 19: FIDELIS (future directions)
Additional grant from CIDA announced on World TB Day (8 million CAD in addition to initial 19 million CAD contribution)
    Funding will ensure available phase II funds for all successful phase I projects
    Round 5 call for phase I applications will take place before summer, 2005
Independent review to assess attribution for all projects
Encourage documentation and publication of both successful and ‘unsuccessful’ approaches
Can FIDELIS approach and process work for other challenging public health problems (e.g. ARV delivery)
Notes: Regarding new money, I would highlight the piece that it will ensure all successful phase I approaches will be scaled up as this is of primary interest to CIDA
Regarding the independent review, I think it is important throughout the case finding data and graphs to emphasize that these are just depictions of the change in case detection during the project and prior to the project and it does not imply attribution (except in some cases as in China where they document that all the additional cases came from the county hospital via the new referral system)
It is the independent review that will look at trends over time, surrounding districts and other funding sources to consider the extent to which additional weighted treatment successes can be attributed to the FIDELIS intervention