## Sheet1
Schedule 2 2-08-14.2B
GDF work plan implementation as of 30 September 2008
No. | Planning Element Title | Planned cost | Budget cost | Expenditure | Impl. rate vs budget cost | Impl. rate vs planned cost
1 | Application review and monitoring | 1983000 | 1249265 | 766293 | 61.34% | 38.64%
2 | Efficient supply of quality GDF products | 72007500 | 69529198 | 50934385 | 73.26% | 70.73%
3 | Procurement and supply activities | 1062000 | 268313 | 146705 | 54.68% | 13.81%
4 | GDF General Management | 1017000 | 423989 | 254941 | 60.13% | 25.07%
| Total | 76069500 | 71470765 | 52102324 | 72.9% | 68.49%